## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
0 | Projekt Setup | Entwicklungsvm, Projekt Setup | high | 10h | 10h | 10h | done
1 | Navigiere zu Patientenadresse |  | low | 10h | 10h | 0h | waiting
2 | Bearbeite ToDo-Liste |  | low | 10h | 10h | 0h | waiting
3 | Zeit erfassen |  | medium | 10h | 10h | 0h | waiting
4 | Spesen erfassen |  | medium | 10h | 10h | 0h | waiting
5 | Zeit bearbeiten |  | medium | 10h | 10h | 0h | waiting
6 | Termin verwalten |  | medium | 10h | 10h | 0h | work in progress
7 | Patienteninformationen anzeigen |  | high | 10h | 10h | 0h | work in progress
8 | Terminerinnerung durchführen |  | low | 10h | 10h | 0h | waiting
9 | Server/Client Synchronisieren (obsolet) |  | none | 10h | 10h | 0h | waiting
10 | Wartung |  | none | 10h | 10h | 0 | work in progress

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
0.01 | 1 | Workspace Setup | Lokale Maven, Eclipse, Vaadin, Tomcat Installation | Development Environment | Swen | high | 6 | 6 | 8 | done
0.02 | 1 | Choose Database | Datenbank muss ausgewählt werden | Development Environment | all | high | 2 | 2 | 2 | done
0.03 | 1 | Split Team | GUI/Core Team | Organisation | all | high | 1 | 1 | 1 | done
0.04 | 1 | Define Interfaces | - | Inital Setup | all | high | 4 | 4 | 0 | done
0.05 | 1 | Statepattern | Informieren | Implementation | all | low | 1 | 1 | 0 | done
0.06 | 1 | Decoratorpattern | Informieren | Implementation | all | low | 1 | 1 | 0 | done
0.07 | 1 | Architektur an Vaadin anpassen | - | Design | all | high | 1 | 1 | 1 | done
0.08 | 1 | Development VM pre Installed DevEnv | - | Inital Setup | Swen | high | 4 | 4 | 0 | done
0.09 | 1 | Initialmodell erstellen | - | Implementation | Pascal B., Swen | high | 1 | 1 | 1 | done
0.1 | 1 | Vaadin kennenlernen, GUI Prototype | - | Implementation | Pascal vO., Roger | high | 8 | 8 | 4 | done
6.01 | 2 | Termin Wechseln | Namen anzeigen | Implementation | Roger | high | 2 | 2 | 0 | work in progress
7.01 | 2 | GUI Design | Patienteninformationen anzeigen | Implementation | Roger | high | 2 | 2 | 0 | work in progress
7.02 | 2 | Erweitern des bestehden Models | An Weiterentwicklung GUI anpassen | Implementation | Pascal B., Swen | high | 2 | 2 | 0 | work in progress
6.02 | 2 | Anzeige korrekturen vornehmen |  | Implementation | Pascal vO | high | 1 | 1 | 0 | work in progress
10.01 | 2 | Classnames English |  | Implementation | Pascal's | high | 1 | 1 | 0 | work in progress
4.01 | 2 | Spesen erfassen |  | Implementation | unassigned | medium | 2 | 2 | 0 | waiting
5.01 | 2 | Zeit bearbeiten |  | Implementation | unassigned | low | 2 | 2 | 0 | waiting
10.02 | 2 | DefinitionOfDone/CodingConventions | Coding Conventions rückwirkend einhalten | Implementation | unassigned | low | 2 | 2 | 0 | waiting