## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Admit new patient | a new patient makes contact on reference from Dr. Boehm. After creating a new patient record, the medical history... | high | 100h | 100h | 0h | waiting
2 |  |  | medium | 200h | 180h | 50h | work in progress
3 |  |  | low | 400h | 450h | 350h | done
4 |  |  | high | 16h | 40h | 12h | cancelled

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Workspace Setup | Lokale Maven, Eclipse, Vaadin, Tomcat Installation | Development Environment | Swen | high | 6 | 6 | 8 | done
1.2 | 1 | Choose Database | Datenbank muss ausgewählt werden | Development Environment | all | high | 2 | 2 | 2 | done
1.3 | 1 | Split Team | GUI/Core Team | Organisation | all | high | 1 | 1 | 0 | work in progress
1.4 | 1 | Define Interfaces | - | Inital Setup | all | high | 4 | 4 | 0 | work in progress
1.5 | 1 | Statepattern | Umsetzen tech Vorgabe | Implementation | all | low |  |  | 0 | work in progress
1.6 | 1 | Decoratorpattern | Umsetzen tech Vorgabe | Implementation | all | low |  |  | 0 | work in progress
1.7 | 1 | Architektur an Vaadin anpassen | - | Design | all | high |  |  | 0 | work in progress
1.8 | 1 | Development VM pre Installed DevEnv | - | Inital Setup | Swen | high | 4 | 4 | 0 | done